## Gantt Chart
Project Gantt Chart – Chapter Work Schedule (2026–2027)
Visual timeline of activities across chapters. Colored cells indicate active work in each period.
Work / Chapter | Dec 2026 – Jan 2027 | Feb – Apr 2027 | May – Jun 2027 | Jul – Aug 2027 | Sep – Oct 2027 | Nov – Dec 2027
Chapter 1 |  |  |  |  | Adaptation | Final draft
Chapter 2 | Publishing | Revision |  |  | Adaptation | Draft
Chapter 3 | Analysis | Analysis | Writing | Writing | Writing | Publishing
Chapter 4 |  | Planning | Lab work | Lab work | Writing | Publishing
Final draft | [5 empty] | Planning
Legend – Activity Types
Publishing |  | Revision |  | Analysis |  | Writing
Lab work |  | Planning |  | Adaptation |  | Final draft / Draft
Notes & How to Edit
• Colored cells show active work in that time period. Empty cells = no scheduled activity.
• To change an activity: simply edit the cell text and apply a matching color from the Legend (or use Format Painter).
• To add a new chapter/row: insert a row above the Legend and copy formatting from an existing task row.
• Time periods can be adjusted in row 4. Keep the same number of columns or extend the range.
• See the 'Data & Bar Chart' sheet for a traditional stacked-bar Gantt that uses start/end dates.
• See the 'Instructions' sheet for more customization tips.

## Data & Bar Chart
Traditional Gantt Chart (Stacked Bar)
This sheet uses approximate start/end dates so Excel can draw a proper stacked-bar Gantt. Edit the dates in columns B–D and the chart will update after recalculation.
Task | Start Date | End Date | Duration (days) | Start Offset (days from project start) | Duration
Ch1 – Adaptation | 2027-09-01 | 2027-10-31 | 61 | 274 | 61
Ch1 – Final draft | 2027-11-01 | 2027-12-31 | 61 | 335 | 61
Ch2 – Publishing | 2026-12-01 | 2027-01-31 | 62 | 0 | 62
Ch2 – Revision | 2027-02-01 | 2027-04-30 | 89 | 62 | 89
Ch2 – Adaptation | 2027-09-01 | 2027-10-31 | 61 | 274 | 61
Ch2 – Draft | 2027-11-01 | 2027-12-31 | 61 | 335 | 61
Ch3 – Analysis | 2026-12-01 | 2027-04-30 | 151 | 0 | 151
Ch3 – Writing | 2027-05-01 | 2027-10-31 | 184 | 151 | 184
Ch3 – Publishing | 2027-11-01 | 2027-12-31 | 61 | 335 | 61
Ch4 – Planning | 2027-02-01 | 2027-04-30 | 89 | 62 | 89
Ch4 – Lab work | 2027-05-01 | 2027-08-31 | 123 | 151 | 123
Ch4 – Writing | 2027-09-01 | 2027-10-31 | 61 | 274 | 61
Ch4 – Publishing | 2027-11-01 | 2027-12-31 | 61 | 335 | 61
Final draft – Planning | 2027-11-01 | 2027-12-31 | 61 | 335 | 61
How the bar chart works:
• Column E (Start Offset) creates the invisible left-hand part of each bar so the colored portion starts at the correct date.
• Column F (Duration) is the visible colored bar showing how long the activity lasts.
• To change dates: edit Start Date (B) or End Date (C). Duration and offset recalculate automatically.
• After editing dates, open the file in Excel or Google Sheets so formulas recalculate and the chart updates.

## Instructions
How to Use & Customize This Gantt Chart
1. Visual Gantt Chart sheet (recommended for overview)
Purpose | Quick visual overview matching your original table. Best for presentations and high-level planning.
Editing activities | Click any colored cell and type a new activity name. Then change its fill color to match the Legend (Home → Fill Color, or Format Painter).
Adding a new chapter | Right-click a row number → Insert. Copy an existing task row and paste, then edit the name and activities.
Changing time periods | Edit the period labels in row 4. If you need more/fewer periods, insert or delete columns and adjust merges if any.
Printing | Set print area to A1:G10 (or adjust), landscape orientation, fit to 1 page wide.
2. Data & Bar Chart sheet (traditional Gantt)
Purpose | Classic floating-bar Gantt that scales with real dates. Useful when you need precise day-level control.
Changing dates | Edit the Start Date or End Date columns (B & C). Duration and offset formulas update automatically.
Adding tasks | Insert a new row in the data table (above the chart). Copy formulas from the row above for columns D–F.
Chart not updating? | Formulas need to be calculated. Open the file in Microsoft Excel, LibreOffice, or Google Sheets; values will appear and the chart will refresh.
Making the offset series fully invisible | In Excel: click the chart → click the left (white) series → Format Data Series → Fill → No fill.
3. Tips for a real project
Dependencies | This template does not enforce task dependencies. Add a 'Predecessor' column if needed and manage sequencing manually.
Progress tracking | Add a '% Complete' column and use conditional formatting or a second overlay series for progress bars.
Milestones | Add rows with 0- or 1-day duration and a distinct color/marker.
Resources | Add a 'Owner' or 'Resource' column next to the task name.
Color reference (hex) | Publishing #C65911 ¦ Revision #70AD47 ¦ Analysis #5B9BD5 ¦ Writing #ED7D31 ¦ Lab work #7030A0 ¦ Planning #00B050 ¦ Adaptation #FFC000 ¦ Final draft #FF0000