## Detailed Gantt
Detailed Project Gantt Chart – Full Chapter Work Schedule (Dec 2026 – Dec 2027)
Chapter / Activity | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | May 2027 | Jun 2027 | Jul 2027 | Aug 2027 | Sep 2027 | Oct 2027 | Nov 2027 | Dec 2027
CHAPTER 1
Thesis final draft | [12 empty] | Thesis draft
CHAPTER 2
Paper drafting | Drafting | Drafting
Submission for publishing | Submission | Submission
Revision based on reviewer feedback |  |  | Revision | Revision
Writing thesis draft | [12 empty] | Thesis draft
Publishing & revision (reviewer feedback)
CHAPTER 3
Virome analysis | Virome analysis | Virome analysis
MAG assembly (Segatella – taxonomic & reference-based) | MAG assembly | MAG assembly
Plasmid identification | Plasmid ID | Plasmid ID | Plasmid ID | Plasmid ID
Novel / homologous uncharacterised gene exploration | Gene exploration | Gene exploration | Gene exploration | Gene exploration
Mapping functional pathways of Segatella |  |  | Pathway mapping | Pathway mapping | Pathway mapping
Outline writing |  |  |  |  | Outline | Outline
Figure generation |  |  |  |  | Figure gen | Figure gen | Figure gen
Writing of first draft | [5 empty] | First draft | First draft | First draft
Redrafting | [11 empty] | Redrafting | Redrafting
Submitting for publishing | [12 empty] | Submission
Publishing & revision (reviewer feedback) | [12 empty] | Revision
CHAPTER 4
Planning (wet-lab in-vitro to verify bioinformatics) |  |  | Planning | Planning | Planning
Segatella isolation from stool samples |  |  |  | Isolation | Isolation
In-vitro verification (metabolic pathways, bacteriocins, AMR, pro-phages) | [5 empty] | In-vitro | In-vitro | In-vitro | In-vitro
Whole genome sequencing of each isolated Segatella species | [5 empty] | WGS | WGS | WGS | WGS
WGS analysis & confirmation (metabolic, secretion, plasmid, prophage) | [7 empty] | WGS analysis | WGS analysis
RNA-seq for expression (if necessary) | [7 empty] | RNA-seq | RNA-seq
Megaplasmid characterisation (if identified) | [7 empty] | Plasmid char | Plasmid char
Cloning of toxin/antitoxin plasmid gene (if present) into E. coli and creating knockouts (if necessary) | [8 empty] | Knockout | Knockout
Finishing lab work / re-running experiments | [9 empty] | Lab finish | Lab finish
Data analysis | [9 empty] | Data analysis | Data analysis
Figure generation | [9 empty] | Figure gen | Figure gen
First draft writing | [10 empty] | First draft | First draft
Publishing & revision (reviewer feedback) | [12 empty] | Revision
FINAL THESIS
Final thesis planning for writing in 2028 and any last data analysis necessary. | [11 empty] | Final planning | Final planning
Legend – Activity Types
Drafting / First draft |  | Submission |  | Publishing |  | Revision |  | Virome analysis |  | MAG assembly
Plasmid ID |  | Gene exploration |  | Pathway mapping |  | Outline |  | Figure gen |  | Redrafting
Planning |  | Isolation |  | In-vitro |  | WGS |  | WGS analysis |  | RNA-seq
Plasmid char |  | Knockout |  | Lab finish |  | Data analysis |  | Thesis draft |  | Final planning